## C2Cislands Work Programme
October 2012 |  |  |  |  | work | plan | sail
year | 2012 | 2012 | 2013 | 2013 | 2013 | 2013 | 2014 | 2014 | 2014 | 2014 | 2015 | 2015
phases | Process, organization & development |  |  | Pilot & implementation | [5 empty] | Finalization & evaluation
| Quarter 3 | Quarter 4 | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | Quarter 1 | Quarter 2
Biannual meetings | Start Meeting: November 2012 Leeuwarden/Harlingen |  |  | 2013-04-01 |  | October 2013 |  |  | 3-6 July 2014 | 2014-11-01 |  | Final Meeting
Project Management | steering group meeting |  | 1 April progress report 1 | steering group meeting | 1 OKTt. progress report 2 | steering group meeting | 1 April 2013 progress report 3 | steering group meeting | 1 September progress report 4 |  | 1 April progress report 5 | last steering group
Financial Managers |  |  | 1 April progress report 1 |  | 1 OKT. 2012 progress report 2 |  | 1April 2012 progress report 3 |  | 1 September progress report 4 |  | 1 April progress report 5 | final report July 2015
Communications
|  | Communications Meeting: |  | Communications Meeting: |  | Communications Meeting: |  | Communications Meeting: |  | Communications Meeting: | Communications Meeting:
Promotional Items | press release | newsletter | press release |  | press release |  | press release |  | press release |  | press release
E-Briefings | September Project Managers E-Briefing | November General E-Briefing | March Project Managers E-Briefing | June General E-Briefing | OKTOBER Project Managers E-Briefing | November General E-Briefing | March: Project Managers E-Briefing | June General E-Briefing
Project Website |  | October Website Reviewed and Updated |  | April Website Reviewed and Updated |  | October Website Reviewed and Updated |  | April Website Reviewed and Updated |  | October Website Reviewed and Updated |  | April Website Reviewed and Updated
Other Activities
workpackage 3
engineering, design pilots, living labs
workpackage 4
economics & implementation
workpackage 5
influencing & integrating policy
workpackage 6
building public private alliances